## Consolidated (hidden)
Story ID | As a | I need to be able to | So that | Phase | Queries/ Exceptions/ Assumptions | NGV comments
NGV 1 | User | View "local deals" for clinics based on geo-location | I can discover nearby deals without signing in | 1 |  | User launches platform on their phone, type in zip code, clinic type, etc, immeditaely populates closest results within a set radius
NGV 2 | User | Create an account and sign in | I can access more personalized deals and select categories & subcategories | 1 | Assumption - "categories & subcategories will be determined/ finalised after extracting treatments/ services using NER"; Query - "Need more input on 'personalized deals'" | Users can browse without signing up, but to checkout or schedule an appointment they must be logged in
NGV 3 | User | See top-rated clinics and explore coupons and deals | I can find the best clinics and offers and read online reviews aggregated under one channel (Yelp, Social & Google) | 1 | Exceptions - For MVP, as agreed only Google reviews will be considered as only Google maps are considered during data extraction process. Other directories will be prioritized in phase 2 | MVP, only google reviews. Future phases, will aggregated 3rd party review platforms
NGV 4 | User | Click on a clinic and select a service and appointment | The clinic can receive my request, schedule the services, and contact me directly | 1 |  | Select clinic ->choose services(s) -> choose appointment date -> appointment schedule with clinic -> pay now or pay at visit? Preference is to pay now, so NGV can collect booking fee, payment processor should linked as part of phase 1 and linked with MVP
NGV 5 | User | View clinic information in no more than 4-5 steps | I can complete my booking or inquiry quickly | 1 |  | Entire booking or checkout process needs to be done in less than 5 steps
NGV 6 | User | Have a luxurious look and feel while finding deals securely | I feel confident in using the app and selecting a clinic that I like | 1
NGV 7 | User | Earn loyalty points when signed in | I am incentivized to create an account | 3 | Since loyalty points has potential dependencies, this is moved to phase 2 | Need to define basic loyalty program first, not a priority moving to phase 3
NGV 8 | User | Access a section for reviews and testimonials and before and after images in an easy to navigate platform | I can see the credibility of different clinics with verified reviews aggregated from google reviews | 1 | Matches with NGV 3. Need more clarity to confirm additional features if any. | User mobile experience should be prioritized in Phase 1. Nedd users to be able to view at least in phase 1, aggregated google reviews. Phase 2 can be other platforms ie. Yelp
NGV 9 | User | Pick from a menu of main health and wellness categories (no more than 5x5 dropdown structure) | I can find relevant services quickly | 1 | Assumption - These will the list of services provided by clinics across Miami for MVP | I will create this first structure and send to you guys
NGV 10 | User | Drill down into subcategories within the main categories | I can refine my search | 1 | Assumption - "categories & subcategories will be determined/ finalised after extracting treatments/ services using NER" | I will create this first structure and send to you guys
NGV 11 | User | List clinics based on location, reviews, deals, and services | I can sort clinics according to my preferences | 2 | Personalization will be focused on phase 2 as MVP holds only one location - Miami | MVP Miami focus
NGV 12 | User | Have a full history of selected services, clinics reviewed, and deals | I can track my past activities and am incentivized to create an account | 1 | Query - Past activities can be recorded for user accounts on the platform. Do you wish to track the activities even before the user starts using the platform? | Lets talk more through this
NGV 13 | User | Receive pop-up alerts for abandoned inquiries or deals | I am reminded of unfinished bookings | 1 |  | This is important and should be part of phase 1 as NGV is incentivized for user to schedule bookings
NGV 14 | User | Access secure payment processing and complete point-of-sale transactions | I can pay for services securely and use coupons and deals accessible only via the app | TBC | Query - How are payments planned to be handled? | Would it be easier to have the clinics process the payment and pay us a fee, or us process payment and send a fee to the clinics? Preference is to have NGV control point of sale
NGV 15 | User | View a detailed clinic profile, including services offered, pricing, and reviews | I can make an informed decision about the clinic | 1 | Query - Will clinics have the ability to change their pricing model? Assumption - For clinics which are scraped & doesn't have an account in NGV App, pricing models will be empty. Such clinics will not be shown to users. | This whole section needs to be based off what the clinic defines. While we will have a lot of data available to us, ultimately a clinic needs to own and maintain their profile. They need to be admins of their profiles/pages - they are customers as well. Ideally, API through clinic CRM automatically updates services and pricing models
NGV 16 | User | Search for clinics using specific keywords or health services | I can find clinics relevant to my needs | 1 |  | SEO driven?
NGV 17 | User | Refine clinic search results based on filters like price, distance, and rating | I can narrow down my search results | 1 | Query - Price attribute will not be publicly available untill clinics start creating accounts in app | Really advanced data schema we will implement - when we get to this story in sprint planning we will work through the specifics. Need to look into CRM integration via API.
NGV 18 | User | Get personalized recommendations based on my preferences and location | I can discover relevant health services easily | 2 |  | Should look into some LLM optimization here
NGV 19 | User | Schedule appointments with clinics directly through the mobile app | I can book services easily without calling the clinic | 1 | Mobile apps will be considered in 3rd phase after web app dev works are complete | The whole platform is mobile first, desktop second
NGV 20 | User | View available time slots and receive booking confirmations | I can secure my appointment time effectively | TBC |  | Integration with clinic CRMs. If they don’t have a CRM, they use our native scheduler or 3rd party?
NGV 21 | User | View and compare special offers from clinics within my desired radius | I can find the best deals in my area | 2 | Since Miami is planned for MVP this feature will be most effective when multiple locations come into play. | Agreed, but remember the entire value proposition of this app for the consumer is for them to find deals at clinics as quickly as possible. That’s the guiding theme
NGV 22 | User | Leave reviews and ratings for clinics I have visited | I can share my feedback with other users | TBC | Query - Need more clarity on "cross pollinate across online platforms" | Lets just keep it to a standard review system for now. Everytime someone leaves a review, they receive +3 loyalty points. If they leave a negative review, +1 loyalty point. If they don’t leave a review, 0 points
NGV 23 | User | Pay for my service or product ahead of time | I can checkout as quickly as possible | 1 | Query - Need more clarity on cancellation, refund, etc | Standard ecommerce process. Monetization strategy for NGV should be part of phase 1 with ability for user to schedule and book appointments and pay for service.
NGV 24 | User | Have the ability to finance my purchase | I can delay the cost while receving the service right away | 3 | Query - Possibilities of financing needs to be discussed. | Integration with some sort of financing/lending partner
NGV 25 | User | Access a dedicated affiliate marketing section | I can explore and participate in marketing opportunities | 1 | Need more inputs on marketing oppurtunities | Ability to share promotions
NGV 26 | Clinic owner | View a dedicated section on the landing page with rotating slides of success stories | I can see the benefits of joining the platform, customer reviews and case studies | 1 |  | This is the Clinic page from their perspective, how they want to showcase and display which services/products on their profile. We need a standard layout for their profiles
NGV 27 | Clinic owner | Trial the platform for free | I can evaluate the platform without commitment | 1 | Trials restrictions has to be confirmed | 1st 5 leads (appointments scheduled) trial, pay after that
NGV 28 | Clinic owner | Have a seamless sign-up process with basic information required | I can join the platform easily and have company lead contact me to learn more about my clinic | 1 |  | Easy for a clinic to sign up, choose their clinic, ensure information is correct (or create their profile), create their first offer and have it go live
NGV 29 | Clinic owner | View rotating images showcasing product manufacturers used in spas | I can visualize potential partnerships and collaborations for trials | TBC | Need more inputs on potential partnerships and collaborations for trials | This is for the ability for clinics to choose or upload images of their products in use
NGV 30 | Clinic owner | Run ads on the platform to gain traction | I can attract more clients to my clinic | 3 | Query - Assume it is the ad of a clinic or vendor, but there is no description about reporting, accounts, types (PPV or PPC), monetization etc. | This is meant to start a campaign in the platform that pushed the campiagn out onto FB, IG, etc
NGV 31 | Clinic owner | Access an affiliate marketing section | I can find potential marketing opportunities | 3 | Need more clarity on application level custom made affiliation program | We really need to define this out, this is the monetization model of the platform in Phase 1
NGV 32 | Clinic owner | Get a live meeting with the company for upsell opportunities | I can explore the full suite of services | 3 | Is this about a live video chat with multiple participants or one-to-one meeting. Are we ready for a third-party services for this feature? | User sees a clinic, can schedule a 1:1 call that turns into a tele-health appointment
NGV 33 | Clinic owner | View catchy images and dialogue surrounding the onboarding process | I feel encouraged to join | 1
NGV 34 | Clinic owner | See branded stories about increased revenue and foot traffic | I am convinced about the benefits of using the platform | 3 |  | This is Clinic advertising to attract more clinics as customer
NGV 35 | Clinic owner | Upload and manage special offers and discounts through an intake system | I can showcase my promotions to potential clients | 1
NGV 36 | Clinic owner | Access an analytics dashboard with insights on user engagement and ROI | I can measure the performance of my marketing campaigns | TBC | Types of "custom marketting campaigns" has to be finalized
NGV 37 | Clinic owner | Access detailed reports showcasing the performance of my specials | I can understand my marketing ROI and track KPIs | 2 |  | Clinic owners need to see the perfomance of their campaigns
NGV 38 | Clinic owner | Track appointment bookings and product sales from my clinic | I can monitor clinic performance directly | 1 |  | Clinic owners need to see the improved lead gen and bookings from the app
NGV 39 | Clinic owner | Integrate with existing clinic appointment scheduling and CRM platforms | I can streamline my operations | 1 |  | Need to integrate with CRMs the top ones such as Vagaro to make it seamless with existing clinic operations
NGV 40 | Clinic owner | Get personalized recommendations based on my location and services offered | I can refine my marketing strategy effectively | 2 | MVP focuses only on Miami, hence moved to phase 2
NGV 41 | Clinic owner | Access a vendor marketplace to discover relevant suppliers | I can find new products and services for my clinic | 3 | Vendor marketplace scope needs to be finalized | Clinics have orders or needs to be filled, they make a posting on the marketplace. Supply chain vendors can then bid on the order from the clinics
NGV 42 | Clinic owner | Have access to a collaborative forum/messageboard (like reddit) where I can connect with other clinic owners | I can keep up with new market trends and have a sounding board | 2 |  | Users can talk to other users, clinics can talk to customers, clinics can talk to each other, vendors can talk to clinics and customers
NGV 43 | Clinic owner | Establish partnerships with supply chain vendors securely | I can negotiate deals and expand my clinic's capabilities | 3 | Partnership feature scoping to be discussed | Last piece of the puzzle, connecting supply chain vendors directly to their clinic customers
NGV 44 | Vendor | Showcase products and services to health clinics through a marketplace | I can reach more clients easily | 3
NGV 45 | Vendor | Access insights on market trends and clinic preferences | I can optimize my product offerings | 3
NGV 46 | Vendor | Integrate my inventory management and order processing systems with the platform | I can manage my clinic orders seamlessly | 3
NGV 47 | Vendor | Access a secure communication channel to connect with clinic owners | I can establish partnerships effectively | 3
NGV 48 | Vendor | Have the ability to bid on clinic orders | I can access a vendor marketplace to fulfill clinic offers (ie. Dermatology clinic needs 10,000 syringes) | 3 | We would need a complete flow properly detailed from generating order list by clinics to bidding by vendors to approval by clinics to payments to delivery | Vendors can bid on clinic orders to be fulfilled. Vendors can offer their own specials direct to clinics that can be fulfilled
NGV 49 | Vendor | Support my customers/clinics 24x7 | I can instantly chat or message clinic owners to provide customer service | 3
NGV 50 | Platform admin | Implement secure user authentication mechanisms like multi-factor authentication and biometric login | I can ensure platform security | 1
NGV 51 | Platform admin | Conduct regular security audits and vulnerability assessments | I can maintain platform integrity | 1
NGV 52 | Platform admin | Monitor user traffic and data processing efficiently | I can ensure optimal performance for all users | 2
NGV 53 | Platform admin | Implement load balancing and caching mechanisms | I can maintain platform responsiveness during peak usage | 1
NGV 54 | Platform admin | Provide a REST API for clinics and vendors | I can support third-party integrations with the platform | 3 |  | Data monetization play, final puzzle piece
NGV 55 | Platform admin | Provide a comprehensive analytics dashboard for clinics and vendors | I can help users make data-driven decisions | 2
NGV 56 | Platform admin | Offer data visualization tools to identify trends and improve performance | I can provide actionable insights | 3
NGV 57 | Platform admin | Enable seamless data exchange between the platform and clinic CRMs | I can simplify data management for clinics | 1 |  | Needs to be phase 1 priority for amazing customer experience
NGV 58 | Platform admin | Conduct regular performance testing and optimization | I can deliver a smooth user experience | 1

## MVP Phase 1 - Features (2) (hidden)
Feature | As a | I need to be able to | Hybrid Dev | Web App | Backend Dev | QA | Total (in days)
Authentication | User | sign up using email and password | 5 | 3 | 3 | 2 | 13
| All users | sign in using email and password
| All users | access forgot password page
| All users | reset password
| All users | change password
| All users | logout
| All users | optionally activate 2 factor authentication
| All users | optionally activate bio-metric authentication
Clinic List | User | View a list of clinics | 8 | 1 | 3 | 2.25 | 14.25
Search for a clinic by name
View a clinic details - name - location - address - contact details - clinic images - services available - opening and closing times - fee range ($, $$, $$$) - deals and coupons - reviews and ratings with images
Sort clinics by their ratings
Sort clinics by distance
Filter clinics by location
Filter clinics by distance range
Filter clinics by category and sub-category
Filter clinics by services
Filter clinics by ratings
Map view (standard implementation - no customizations)
Deals and Coupons List | User | View a list of deals and coupons | 4 | 1 | 2 | 1.25 | 8.25
Filter deals and coupons by distance range
View a deal details
Compare deals from clinics within selected radius
Select a deal or use a coupon - this should take me to appointment booking page - the deal should automatically be applied
Appointments | User | View available time slots for a clinic | 4 | 1 | 2 | 1.25 | 8.25
Book a time slot by providing following details - patient name, age and other required details - service required
Apply deals or coupons, if any
|  | Use loyalty points, if any | lets talk thorugh this
|  | Make payment and confirm booking | lets talk thorugh this
View a list of all appointments I have made
View an appointment details - clinic name - clinic address and location - booking date-time - appointement date-time - payment status
Action tracking | User | list of past searches | 1 | 0 | 1 | 0.25 | 2.25
receive notification for incomplete bookings
Alerts and Notifications | User | Receive a booking confirmation notification | 1 | 1 | 3 | 1 | 6
Receive a payment receipt
Receive pop-up alerts for abandoned inquiries or deals
View a list of all notifications
Perform actions based on notification type
Receive reminder alerts about coming scheduled appointments
Receive payment alerts if I have not paid already for an appointment
Receive personalized recommendations
Receive an appointment cancellation notification
Profile and preferences | User | View my profile - name - email - Phone - Address (location from Map) | 2 | 0.5 | 1 | 0.625 | 4.125
Update my profile
Payments |  | Make a payment | 3 | 1 | 3 | 1 | 8 | POS integration with clinic CRMs like Vagaro
|  | View my payment history | [5 empty] | yes integration with 3rd party lender
View available balance
View balance loyalty points
Ratings and reviews | User | Rate and review a clinic | 2 | 0.5 | 1 | 1 | 4.5
Rate and review a service separately with following - rating from 1 to 5 - review text - images
View all my ratings and reviews along with uploaded images
Clinic Onboarding | Clinic Owner | Create an account with all details - name - location - address - contact details - clinic images - services available - opening and closing times - fee range ($, $$, $$$) - deals and coupons - reviews and ratings with images (not editable) | 2 | 10 | 3 | 3 | 18
|  | Claim a clinic which is already available on the platform | We will initially harvest all clinic data ourselves, when a clinic registers for the 1st time they should be able to "claim" their clinic based off our data and be the admin of it.
Get a trial period of free access of the platform
|  | Become a premium user by making a payment | We havent defined premium users yet. Just guest and sign up users
View success stories (of other clinics) on the platform (rotating slides)
View product manufacturers used in spas (rotating slides)
See branded stories about increased revenue and foot traffic
Appointment Management | Clinic Owner | Create appointment schedules (time slots) | 5 | 1 | 3 | 1.5 | 10.5 | Yes work with existing CRMs where possible
View appointment schedule
|  | View all appointment bookings | [5 empty] | As a clinic owner, I should be able to view a historical time period of performance of my clinic in the app. how many appointments did I book this month, which services were booked, my revenue, etc.
Delete an appointment slot (before booking)
View a booked appointment details - slot details - patient details - payment details
Cancel a booked appointment (in case of emergency) - a notification will be sent to the patient (user) - payment will be returned to the user
Reschedule a booked appointment - a notification will be sent to the patient (user)
Deals Management | Clinic Owner | Create deals - title - offer details - image - service | 1 | 3 | 1 | 1 | 6
Update deals
Delete deals
List deals
Deals reports - reports of deal usage based on date-time, deal, service, and user
Misc | Clinic owner | Get personalized recommendations based on my location and services offered | 0.5 | 2 | 2 | 1 | 5.5
| Platform admin | Provide a comprehensive analytics dashboard for clinics and vendors | 0 | 12 | 5 | 3 | 20
User management and reports
Clinic management and reports
Content management and reports
|  |  | Total Efforts (In days) |  |  |  | 128.625
What is not included (As we need more clarification on the user stories): - Advertisements - Affiliate marketing - Financing purchase - Live meeting (customer support for clinics and vendors for admins), vendors to clinics, clinics to users. all text chat for now + chat bot - Integration with existing CRMs - Collaborative Forum - Vendor related stories Please check the red cells in "User Stories" sheet for excluded user stories. Security and caching related user stories under Platform Admin are not added, as they are part of development. Analytics related few stories are not added. As we get more clarification on vendors we would be able to invision what other data we are generating and how to analyse them.

## Exclusions (hidden)
As a | Able to
User | Have the ability to finance my purchase
User | Access a dedicated affiliate marketing section
Clinic owner | Run ads on the platform to gain traction - Create add campaign with title, description, image, start date, end date, frequency - Make payment - Ad tracking (views, clicks) - Show ads (with an algo) - Ad reports over all, campaign wise
Clinic owner | Get a live meeting with the company for upsell opportunities - Integrate a chat API with chat bot
Clinic owner | Access an analytics dashboard with insights on user engagement and ROI
Clinic owner | Integrate with existing clinic appointment scheduling and CRM platforms
Clinic owner | Access a vendor marketplace to discover relevant suppliers
Product List - name, description, category, sub-category, images, price, offer - search, filter, sorting
Product details
Add to order list
Send for bidding
View bids, accept
Clinic owner | Have access to a collaborative forum/messageboard (like reddit) where I can connect with other clinic owners
Chat Room/group management - create with name, avatar, description, rules - update details - delete a room/group - view my group list
View group list
View group members
View group posts
Join a group as a member
Create a post with text and image
Comment on posts
React on posts
Delete a post
Delete a comment
Remove a member
leave a group
Clinic owner | Establish partnerships with supply chain vendors securely
Vendor | Manage account and profile
View
Edit
Vendor | Showcase products and services to health clinics through a marketplace
Product management - name, description, images, price
Vendor | Access insights on market trends and clinic preferences
Vendor | Integrate my inventory management and order processing systems with the platform
Vendor | Access a secure communication channel to connect with clinic owners - one to one live text chat (using a third party service e.g. MirrorFly, Twilio)
Vendor | Have the ability to bid on clinic orders
View list of orders (in specific area)
View order details
Bid on order
View a list of all my bids
View winning bids
Vendor | Support my customers/clinics 24x7 - considering a customer support is already implemented for super admin
Platform admin | Vendor management and reports
Bids management and reports
Subscription management and reports
Ads management and reports
User | receive loyalty points on sign-up
User | Make a payment
View my payment history
View available balance
View balance loyalty points

## MVP Phase 1 - Features
Feature | As a | I need to be able to | Hybrid Dev | Web App | Mobile App | Backend Dev | QA | Total (in days) | Milestone
Authentication & Role Access | All roles | Design login & landing screen flows for each role (mobile + web-lite)
Authentication & Role Access | All roles | Implement login form validations, error states and session timeout UI
Authentication & Role Access | All roles | Implement forgot password & reset flow UI (email/OTP)
Authentication & Role Access | All roles | Implement role-based landing/dashboard routing (UI rules)
Task & Schedule Management | Technician / Team Lead | Design task list UI (cards, filters: Today/Upcoming/Completed)
Task & Schedule Management | Technician / Team Lead | Build task card component with status badges and quick actions
Task & Schedule Management | Technician / Team Lead | Task detail screen: checklist UI, notes, scheduled time, attachments
Task & Schedule Management | Technician / Team Lead | Implement start/stop task local state handling (UI only)
Task & Schedule Management | Technician / Team Lead | Reschedule task UI: date/time picker, conflict warning messages
Task & Schedule Management | Technician / Team Lead | Reassign technician UI (single & bulk) with reason input
Task & Schedule Management | Technician / Team Lead | Task list offline placeholder & pending sync indicators (UI)
Task & Schedule Management | Technician / Team Lead | Loading skeletons, empty states and error states for task flows
Inspection & Quality Scoring | Team Lead | Design inspection checklist UI (configurable fields placeholder)
Inspection & Quality Scoring | Team Lead | Rating control (1-5) UI with mandatory comment/photo enforcement if configured
Inspection & Quality Scoring | Team Lead | Attach photos & remarks UI in inspection flow (capture + gallery)
Inspection & Quality Scoring | Team Lead | Inspection submit flow: local validation, confirmation UX
Inspection & Quality Scoring | Team Lead | Inspection history view on task detail (show previous scores & notes)
SLA & Corrective Ticketing | Team Lead / Ops Admin | SLA ticket summary UI: status, due date, SLA progress bar
SLA & Corrective Ticketing | Team Lead / Ops Admin | Ticket detail view: proofs, comments, reopen/return buttons
SLA & Corrective Ticketing | Team Lead / Ops Admin | Create 'return for rework' UI with reason input and notifications trigger
SLA & Corrective Ticketing | Team Lead / Ops Admin | SLA notifications handling UI (50% and 100% thresholds)
SLA & Corrective Ticketing | Team Lead / Ops Admin | Ticket list filters and search (by site, status, date)
Feedback & Client Actions | Client | Feedback form UI: rating control, comment box, attach media option
Feedback & Client Actions | Client | Media picker UI & validation (max files, size limit) with previews
Feedback & Client Actions | Client | Reopen ticket UI: select closed ticket, provide reason, submit
Feedback & Client Actions | Client | Create sub-ticket UI from parent ticket: category selector, description
Feedback & Client Actions | Client | Client ticket list and SLA progress view in client dashboard
Site Verification (GPS/QR/Site Access Code) | Technician / Ops Admin | Design site verification settings UI in web-lite (admin toggle per site)
Site Verification (GPS/QR/Site Access Code) | Technician / Ops Admin | QR code scanner UI and result handling (scan + verify locally)
Site Verification (GPS/QR/Site Access Code) | Technician / Ops Admin | Site Access Code entry UI with copy/paste protection & validation UX
Site Verification (GPS/QR/Site Access Code) | Technician / Ops Admin | GPS permission prompt and geofence indicator on mobile task screen
Site Verification (GPS/QR/Site Access Code) | Technician / Ops Admin | Verification failure flows and escalation prompts in UI
Form Builder (Static & Dynamic fields) | Ops Admin | Design form builder UI: template creation wizard & field palette
Form Builder (Static & Dynamic fields) | Ops Admin | Add static fields (predefined) UX and preview mode
Form Builder (Static & Dynamic fields) | Ops Admin | Add dynamic field creation UI: dropdowns, text, numeric, date
Form Builder (Static & Dynamic fields) | Ops Admin | Work order template selection flow and field mapping preview
Form Builder (Static & Dynamic fields) | Ops Admin | Field ordering, validation rule UI, and save/publish template actions
Work Orders & Contracts (creation) | Ops Admin / Super Admin | WO creation screen: select template, fill dynamic fields, assign team
Work Orders & Contracts (creation) | Ops Admin / Super Admin | Attach site access code and verification mode selection UI
Work Orders & Contracts (creation) | Ops Admin / Super Admin | Schedule periodicity setup UI and calendar preview
Work Orders & Contracts (creation) | Ops Admin / Super Admin | WO save confirmation, edit, and clone functionality UI
Site Access Code Management | Ops Admin / Super Admin | Generate site access code UI and assignment modal for janitors
Site Access Code Management | Ops Admin / Super Admin | Code revocation UI and audit log link
Site Access Code Management | Ops Admin / Super Admin | Code usage list view and search/filter by janitor/site/date
Proof Upload & Evidence | Technician / Team Lead / Client | Camera capture UI: photo & short video capture flows
Proof Upload & Evidence | Technician / Team Lead / Client | Gallery picker & multi-select upload preview UI
Proof Upload & Evidence | Technician / Team Lead / Client | Local storage placeholder + queued uploads indicator (UI)
Proof Upload & Evidence | Technician / Team Lead / Client | Proof metadata display (timestamp, uploader, site code) inside task/ticket
Proof Upload & Evidence | Technician / Team Lead / Client | Image/video compression settings UI control (client side) and error feedback
Offline Sync & Media Handling | Technician | Pending-sync list UI and retry buttons for failed uploads
Offline Sync & Media Handling | Technician | Background sync status indicator and toast messages
Offline Sync & Media Handling | Technician | Conflict UI for local vs. remote edits (show options to keep local or overwrite)
Offline Sync & Media Handling | Technician | Offline form entry placeholders and autosave indicators |  |  |  | We havent defined premium users yet. Just guest and sign up users
Notifications & Audit Trail | All roles | Notification center UI: list of in-app notifications and filters
Notifications & Audit Trail | All roles | Push notification opt-in prompts and settings UI
Notifications & Audit Trail | All roles | Audit trail viewer (web-lite): chronological actions with media links
Notifications & Audit Trail | All roles | Notification deep-link behavior in-app to open exact task/ticket |  |  |  | Yes work with existing CRMs where possible
Reassign & Reschedule (single & bulk) | Team Lead | Bulk selection UI for multiple tasks and reassignment flow
Reassign & Reschedule (single & bulk) | Team Lead | Single task reassignment modal with reason input |  |  |  | As a clinic owner, I should be able to view a historical time period of performance of my clinic in the app. how many appointments did I book this month, which services were booked, my revenue, etc.
Reassign & Reschedule (single & bulk) | Team Lead | Conflict detection notifications and resolution UI
Global Oversight (Web-lite) | Super Admin | Minimal summary list UI of open escalations and SLA hotspots
Global Oversight (Web-lite) | Super Admin | Override closure UI: reason input modal and confirmation flow
Global Oversight (Web-lite) | Super Admin | Audit trail search UI and export/print placeholder
Lets talk through these

## User Stories - Phase 1 (hidden)
As a | I need to be able to | So that
Technician | View all assigned daily/weekly tasks including task type, location, and schedule | I can plan my workload and complete tasks in the correct order
Technician | Verify presence using GPS/QR/Site Access Code before starting a task | tasks only start when I am physically present at the site
Technician | Open task details including checklist, notes, and instructions | I can perform the task correctly as required
Technician | Capture and upload photos/videos with timestamps | team leads and clients can validate my work
Technician | Work offline and sync my updates later | my work continues even in low-network areas
Technician | View my past 30 days of tasks with proof | I can reference previous work when needed
Team Lead | View all technician tasks with real-time status | I can monitor daily site operations
Team Lead | Assign or reassign tasks (single/bulk) | I can balance manpower and adjust for delays
Team Lead | Reschedule task timings with reasons | operational issues can be handled smoothly
Team Lead | Perform inspections with dynamic checklist, rating, comments, and media | I can evaluate quality effectively
Team Lead | Automatically trigger SLA tickets on low scores | corrective actions begin immediately
Team Lead | Receive SLA countdown and breach alerts | I can prevent SLA violations
Client | View ongoing and completed tasks for my site | I have transparency on service delivery
Client | View proof submitted for completed tasks | I can confirm work quality
Client | Submit ratings, comments, and attachments | I can share satisfaction or concerns
Client | Reopen a closed ticket with a reason | unresolved issues can be addressed again
Client | Create sub-tickets under an existing ticket | related issues are tracked together
Client | View SLA countdown and progress | I understand resolution timelines
Ops Admin | Configure static & dynamic form fields | work orders and forms match site needs
Ops Admin | Create work orders with verification rules | sites are provisioned correctly
Ops Admin | Review SLA tickets with submitted proof | I can approve or request rework
Ops Admin | Return tickets for rework | quality standards are maintained
Ops Admin | Generate, assign, and revoke site access codes | technicians verify presence securely
Super Admin | View all escalated SLA tickets & site performance | I can ensure company-wide service quality
Super Admin | Override or finalize escalated tickets | critical issues are resolved promptly
Super Admin | View audit trails for all actions | transparency and accountability are maintained
Ops Admin/Super Admin | Create new employee records (name, email, phone, role, assigned property) | new staff members can be added and start using the system.
Ops Admin/Super Admin | view a list of employees with filters (role, status, property,area assigned and task assigned) | I can manage the workforce efficiently.
Ops Admin/Super Admin | view individual employee profiles (assignments, contact, status) | I can validate who is assigned where.
Ops Admin/Super Admin | update employee information (role, property assignment, contact details) | employee records reflect current reality
Ops Admin/Super Admin | deactivate or delete an employee | former staff do not appear in assignments and cannot log in
Ops Admin/Super Admin | create a property (name, address, client, site rules) | a location can be included in work orders
Ops Admin/Super Admin | view all properties with search and filters | I can find locations quickly.
Ops Admin/Super Admin | view full property details (areas, geofence, access code) | I can understand site configuration
Ops Admin/Super Admin | edit property information | changes in client details are reflected
Ops Admin/Super Admin | deactivate a property when a contract ends | it is not included in active scheduling
Ops Admin/Team Lead | create areas at a property level if required by contract (or allow Team Lead to create areas) | site layout can be defined.
Ops Admin/Team Lead | create areas (e.g., room1, bathroom, kitchen, meeting room) under a property | the team can have zone-level checklists and assignments
Ops Admin/Team Lead | view areas for a property | I can check the zones requiring cleaning
Ops Admin/Team Lead | edit area details (name, floor, zone) | the structure is correct
Ops Admin/Team Lead | deactivate an area | unused zones do not appear in WOs.
Team Lead | create task definitions for an area (e.g., clean window, clean urinals, refill soap) | technicians have a clear checklist
Team Lead | view all tasks linked to an area | I can confirm the checklist is complete
Team Lead | edit area-level tasks (rename, instructions, frequency) | task detail stays accurate
Team Lead | deactivate area tasks | deprecated tasks do not show up on checklists
Team Lead | assign technicians to area tasks (single & bulk) and reschedule them | the team executes tasks efficiently and responsively

## User Stories - Phase 1 (Updated
User Role | Menu Item | User Action | Action Result | Hybrid Dev | Web App | Mobile App | Backend Dev | QA | Total (in days) | Milestone
Technician | Dashboard | View today’s tasks | I can see all tasks scheduled for today under my active contract.
Technician | Dashboard | Tap locked task | I am redirected to the Check-In screen if access verification is required.
Technician | Dashboard | Start a task | I can begin the task only when in the allowed scheduled time window.
Technician | Dashboard | Open task detail | I can view checklist, photos, notes, supplies, and signature requirements.
Technician | Dashboard | Complete checklist items | I can fill responses based on contract template requirements.
Technician | Dashboard | Upload proof photos | I can provide mandatory or optional proof images for the task.
Technician | Dashboard | Add task notes | I can document any observations related to the task.
Technician | Dashboard | Log supplies used | I can record materials consumed for the task.
Technician | Dashboard | Save task as draft | I can save progress and continue later.
Technician | Dashboard | Complete task | I can submit the task once all required fields are completed.
Technician | Scheduled Tasks | View upcoming tasks | I can view tasks scheduled for future dates.
Technician | Scheduled Tasks | Tap locked scheduled task | I am redirected to Check-In if early access is restricted.
Technician | Scheduled Tasks | Open scheduled task detail | I can see what’s planned for future work.
Technician | My Tickets | View assigned tickets | I can see all SLA tickets assigned to me.
Technician | My Tickets | Add ticket comment | I can update supervisors with progress or notes.
Technician | My Tickets | Upload ticket photo | I can attach supporting images for ticket handling.
Technician | My Tickets | Resolve ticket | I can complete the ticket if assigned by TL or Supervisor.
Technician | Supply Request | Submit supply request | I can request inventory items needed for my work.
Technician | Supply Request | Select property/area | I can specify which location needs the supplies.
Technician | Supply Request | Choose SKU and quantity | I can request allowed supply items under the contract.
Technician | Notifications | View notifications | I can see alerts for tasks, tickets, and updates.
Technician | Notifications | Tap notification | I am redirected to the related task or ticket detail.
Technician | Offline Sync | View offline queue | I can see pending sync items when offline.
Technician | Offline Sync | Retry sync | I can manually push unsynced data once network returns.
Technician | Profile | Edit profile information | I can update my name and email.
Technician | Profile | View assigned contracts | I can see all contracts I belong to.
Technician | Profile | Set default contract | I can make the app load my preferred contract by default.
Technician | Profile | Change password | I can update my login credentials.
Technician | Help & Support | View help topics | I can read quick help and guidance.
Technician | Help & Support | Submit support ticket | I can report issues related to the app or site.
Technician | Help & Support | View my support ticket history | I can track support tickets and responses.
Technician | Check-In (Triggered) | Enter access code | I can unlock site tasks for that scheduled event.
Technician | Check-In (Triggered) | Verify code | I can start work after successful verification.
Technician | Authentication | Sign in | I can securely access my dashboard.
Technician | Authentication | Reset password | I can recover access if credentials are forgotten.
Technician |  | Verify presence using GPS (Optional) | the system can confirm I am physically at the correct site before I start the task.
Technician |  | Verify presence using QR scan (Optional) | I can easily check in at the site using a scannable code placed there.
Technician |  | Verify presence using Site Access Code | I can authenticate my presence even when GPS/QR is not available.
Ops Admin |  | Configure site verification mode | each property can enforce the appropriate verification method (GPS/QR/Code) based on operational needs.
Proof Upload & Evidence
Technician |  | Capture photos as proof | I can show visual evidence of the work completed at the site.
Technician |  | Upload media files | proof is attached to the task and visible to Team Leads and Clients.
Technician |  | Retry failed uploads (offline sync) | I can submit proof even after returning to network coverage.
Team Lead |  | Review proof uploaded by technician | I can assess the quality and completeness of the task performed.
Client |  | View proof for completed tasks | I can verify that the cleaning work meets expectations.
Inspection & Quality Scoring
Team Lead |  | Open inspection checklist | I can review the required inspection steps for the area.
Team Lead |  | Rate service (1–5) | I can provide a quantitative score for task quality.
Team Lead |  | Add inspection remarks | I can give specific feedback or highlight issues.
Team Lead |  | Attach inspection photos/videos | I can document evidence of quality or issues found.
Team Lead |  | Submit inspection results | the system records inspection status and triggers corrective actions if needed
SLA & Corrective Ticketing
Team Lead |  | View SLA tickets | I can monitor issues that require immediate corrective action.
Team Lead |  | Receive SLA warning notifications | I am alerted when an SLA is nearing a breach and can act promptly.
Team Lead |  | Return ticket for rework | I can ensure incomplete or poor-quality work is corrected.
Ops Admin |  | Approve SLA ticket closure | I can confirm issues have been properly resolved before closing.
Ops Admin |  | Send ticket back for rework | I can enforce quality standards and ensure issues are addressed thoroughly.
Super Admin |  | Override escalated SLA tickets | I can resolve critical issues that require top-level intervention and finalize decisions.
Feedback, Reopen & Sub-ticket (Client)
Client |  | Submit service rating | I can share my satisfaction level with completed work.
Client |  | Write feedback comments | I can provide detailed input on the quality of service.
Client |  | Upload feedback media | I can visually demonstrate issues or appreciation.
Client |  | Reopen a closed ticket | I can get further assistance if the original issue wasn't resolved fully.
Client |  | Create a sub-ticket | related or follow-up issues can be tracked under the same case.
Client |  | View SLA progress on tickets | I know how long it will take to resolve the issue.
Ops Admin |  | Add static fields to form | mandatory fields from the Site Visit standard can be included in work orders.
Ops Admin |  | Add dynamic fields to form | I can customize forms based on property-specific requirements.
Ops Admin |  | Reorder fields | I can organize the form layout for clarity and operational flow.
Ops Admin |  | Save form template | I can reuse standardized forms for multiple properties or contracts.
Ops Admin |  | Publish form template | the form becomes available for generating work orders.
Work Orders & Contracts Creation
Ops Admin |  | Create work order using existing contract template | I can quickly generate a structured plan for cleaning activities at a property.
Ops Admin |  | Define verification mode (override) | I can enforce the required site-entry validation method for each work order.
Ops Admin |  | Assign team lead & technicians | the correct staff are responsible for executing the tasks defined in the work order.
Ops Admin |  | Set periodic schedules | tasks repeat automatically based on contract terms and operational frequency.
Site Access Code Management
Ops Admin |  | Generate site access code | technicians can authenticate their presence before starting tasks.
Ops Admin |  | Revoke existing access code | I can disable outdated or compromised access codes.
Ops Admin |  | Assign code to janitor | only authorized staff can perform tasks at that property.
Ops Admin |  | View usage history | I can track who accessed the site and when verification happened.
Offline Sync & Media Handling
Technician |  | Use app in offline mode | I can continue working even without network coverage.
Technician |  | Save pending uploads | my task data and proof can be stored until the network is restored.
Technician |  | Retry uploads when connected | proof and updates sync automatically once internet returns.
Technician |  | Handle upload conflicts | my data stays accurate even if multiple edits happen before syncing.
Notifications & Alerts
All roles |  | Receive notifications for tasks | I stay informed about newly assigned or updated tasks.
All roles |  | Receive SLA threshold alerts | I know when an SLA is close to breaching and can take timely action.
All roles |  | Receive assignment updates | I am aware of changes in my task responsibilities.
All roles |  | Open notifications via deep link | I can go directly to the relevant screen for faster action.
Audit Trail & Activity Logs
Ops Admin |  | View audit logs | I can see who performed key actions within the system for accountability.
Super Admin |  | Search audit logs | I can find specific activities or events when required.
Super Admin |  | Export audit logs | I can store or analyze logs outside the system for compliance or reporting.
Employee Management
Ops Admin / Super Admin |  | Create employees | new staff can be onboarded and assigned roles.
Ops Admin / Super Admin |  | View employees | I can review all users and their statuses.
Ops Admin / Super Admin |  | Edit employees | employee details can stay updated and accurate.
Ops Admin / Super Admin |  | Deactivate employees | inactive staff no longer have system access.
Property Management
Ops Admin / Super Admin |  | Create properties | cleaning operations can be set up for new client locations.
Ops Admin / Super Admin |  | View properties | I can monitor all operational client sites.
Ops Admin / Super Admin |  | Edit properties | property details remain up to date.
Ops Admin / Super Admin |  | Deactivate properties | inactive sites do not appear in operational workflows.
Area Management
Ops Admin / Team Lead |  | Create areas | properties can be organized into cleanable zones.
Ops Admin / Team Lead |  | View areas | I can see the structure of each property.
Ops Admin / Team Lead |  | Edit areas | changes in layout are reflected correctly.
Ops Admin / Team Lead |  | Deactivate areas | obsolete areas are removed from operation.
Task Management
Ops Admin / Team Lead |  | Create tasks for areas | technicians know the exact cleaning steps required.
Ops Admin / Team Lead |  | View tasks | I can confirm the checklist for each zone.
Ops Admin / Team Lead |  | Edit tasks | task requirements stay accurate as needs change.
Ops Admin / Team Lead |  | Deactivate tasks | outdated or irrelevant tasks are removed.
Contract Management
Ops Admin / Super Admin |  | Create a new contract record (single form) | a formal agreement can be set up between the company and the client.
Ops Admin / Super Admin |  | View contract details and history | I can track contract terms and past versions.
Ops Admin / Super Admin |  | Edit/update contract master data (dates, client, notes) | contract information remains current and accurate.
Ops Admin / Super Admin |  | Deactivate or archive a contract | expired or completed contracts do not affect active operations.
Ops Admin / Super Admin |  | Upload contract document (PDF) and attach to record | legal documents are stored centrally within the system.
Ops Admin / Super Admin |  | Bulk import contracts via CSV/XLSX | multiple contracts can be onboarded efficiently.
Ops Admin / Super Admin |  | Preview import file and validate rows | I can correct errors before import.
Ops Admin / Super Admin |  | Import report with success / failed rows | I know which contracts were successfully processed.
Ops Admin / Super Admin |  | Download contract import template | I follow the correct format during bulk uploads.
Ops Admin / Super Admin |  | Map import columns to contract fields | I can import files even when headings differ.
Ops Admin / Super Admin |  | Link contract to one or more Property IDs | contract scope covers the correct sites.
Ops Admin / Super Admin |  | Set default verification mode for a contract | Work Orders inherit the correct verification rules.
Ops Admin / Super Admin |  | Generate and assign Site Access Codes | technicians can access sites securely per contract.
Ops Admin / Super Admin |  | Set SLA terms or reference an SLA template | response timelines are defined per contract.
Ops Admin / Super Admin |  | Assign primary Ops contact / AssignedTeam | contract responsibility is clearly designated.
Ops Admin / Super Admin |  | Search and filter contracts | I can quickly find contract records.
Ops Admin / Super Admin |  | Approve or override contract changes | sensitive updates can be controlled.
Ops Admin / Super Admin |  | View contract version history and audit trail | I can trace what changed and when.
Ops Admin / Super Admin |  | Export contract list (CSV/Excel) | I can analyze or store contract data offline.
Ops Admin / Super Admin |  | Validate PropertyIDs during import | incorrect property mappings are prevented.
SUPPLIES REQUEST & INVENTORY INTEGRATION
Technician |  | Raise a supplies request from Mobile App | Request submitted to Supervisor/Admin for approval
Team Lead |  | Raise supply request for the team | Request created with item list, qty, photos
Supervisor |  | Approve or reject supply requests | Inventory updated if approved; requester notified
Operations Admin |  | View and manage inventory levels | Can add/adjust stock, view usage logs
Operations Admin |  | Deduct inventory on approval | Stock decreases; audit log updated
Supervisor/Admin |  | View low-stock alerts | System notifies when inventory drops below threshold
SITE VISIT MODULE (AD-HOC, ONE-TIME SERVICE)
DIFFERENTIATION
Contract Tasks = recurring (Daily/Weekly/Monthly)
Site Visit = one-time / on-demand / issue-driven (NOT task schedule related)
Team Lead |  | Create Site Visit | Visit is logged with type and site details
Supervisor |  | Create/Assign Site Visit | Visit appears in assigned user schedule
Team Lead |  | Select Visit Type (One-time/Emergency/Complaint/Other) | Type stored and used for SLA classification
Team Lead |  | Upload photos & notes during visit | Photos stored and linked to visit record
Supervisor |  | Flag potential work orders (Example: Dumpster Overflow, Carpet Cleaning etc.) | Work order flagged for Ops Admin review
Supervisor |  | Add follow-up actions & dates | Follow-up tracked until resolved
System |  | Auto-differentiate visit from recurring contract task | Displays separate module “Site Visits” in app/web

## Menu & Field List - TECHNICIAN
User Role | Main Menu Option | Screen / Context | Field Label | UI Control Type | Placeholder / Example | Required? | Assigned By | Validation / Notes | Mobile App (hrs) | Backend Dev (API) | QA | Total (IN Hrs) | MIlestones
Technician (Field Staff) | Authentication (Pre - Login) | Sign-In | Phone Number | Text Input (numeric keypad) | “Enter mobile number” | Yes | System | Must be E.164 format or local format; validate registered user; show inline error if not found. | 4 | 2 | 1 | 7
|  |  | Password | Password Field | “Enter password” | Yes | System | Masked; show “Show/Hide” toggle; min 8 chars, server-side validation.
|  |  | Forgot Password Link | Link | “Forgot Password?” | No | System | Sends OTP or password-reset link depending on your Phase-1 design.
|  |  | Sign-In Button | Button | “Sign In” | Yes | System | On click → authenticate → retrieve contracts → redirect to Contract Selector (if >1) or Dashboard (if only 1).
|  | Forgot Password | Phone Number | Text Input | “Enter mobile number” | Yes | System | Validate that user exists. | 4 | 2 | 1 | 7
|  |  | Send OTP | Button | “Send Code” | Yes | System | OTP delivered via SMS.
|  |  | OTP Input | PIN Input (6-digit) | “Enter OTP” | Yes | System | Retry allowed; rate-limit OTP requests.
|  |  | New Password | Password Input | “Create new password” | Yes | System | Validate password rules.
|  |  | Confirm Password | Password Input | “Re-enter password” | Yes | System | Must match.
|  |  | Reset Button | Button | “Reset Password” | Yes | System | On success redirect to Sign-In.
|  | OTP Verification (if 2FA enabled) | OTP Field | PIN Input | “Enter verification code” | Yes | System | Only shown if 2FA toggle enabled by user in Profile. |  | 0
|  |  | Resend Code | Button | “Resend” | No | System | Apply resend delay and rate limit. |  | 1 | 0 |  | 1
| Contract Filter - (Not a Menu Option) | Contract Header | Contract List | Dropdown | “XYZ Tower – Recurring Contract” | Yes if >1 | System / Ops Admin | Switch reloads ALL contract-scoped data (properties, areas, tasks, schedule, rules).
|  |  | Contract Type | Badge | “Recurring / Ad-Hoc” | Yes | System | Enforces feature toggles for tasks, supplies, photos, checklists.
|  |  | Contract Duration | Text | “Valid: Jan–Dec 2026” | Yes | System | Display only.
| Dashboard | Task Cards | Today’s Tasks List | Card List | — | Yes | System | Load ONLY tasks where task.contract_id == active_contract.id
|  |  | Property | Text | “XYZ Tower” | Yes | System | Display only.
|  |  | Area | Text | “Ground Floor Lobby” | Yes | System | Display only.
|  |  | Task Type | Text | “Daily Mopping” | Yes | System | From contract template.
|  |  | Scheduled Time | DateTime | 11/26/2025 - 10:15 AM | Yes | System | Local timezone.
|  |  | Status | Badge | “Locked / To Do / In Progress” | Yes | System | If check-in required & not verified → show “Locked”.
|  |  | Checklist Summary | Pill | “2/5 Done” | Cond | System | Visible ONLY if task is unlocked.
|  |  | Photo Count | Icon + count | “2 photos” | Cond | System | Visible ONLY if unlocked.
|  |  | Start Button | Button | “Start” | Cond | System | Visible ONLY if unlocked.
|  |  | Tap Action | Touch → Navigation | — | Yes | System | If task is locked → redirects to Check-In Screen.
|  | Task Detail - Main | Property | Text | “XYZ Tower” | Yes | System | Display only.
|  |  | Area | Text | “Basement Parking - Zone A” | Yes | System | Display only.
|  |  | Task Type | Header | “Daily Mopping” | Yes | System | Based on contract template.
|  |  | Scheduled Window | Label | “Window: 09:00–11:00” | Yes | System | Start allowed only inside window.
|  |  | Start Task | Button | “Start Task” | Cond | System | Visible only if unlocked + within window.
|  | Task Detail - Checklist | Checklist (inline accordion) | Accordion | — | Cond | System | Loaded from template configured for this area+task under active contract.
|  |  | Item Label | Text | “Sweep floor” | Yes | System | Template-defined.
|  |  | Response | Radio/Text/Dropdown | “Yes / No / N/A” | Cond | System | Required if template says so.
|  |  | Item Photo | Camera Button | “Attach photo” | Cond | System | Required if contract template says requires_photo.
|  | Task Detail - Photos | Task-level Photo Upload | Camera/Gallery | “+ Add Photo” | Cond | System | Photos required if active_contract.proof_required==true
|  |  | Thumbnails | Image Preview | — | No | System | Remove allowed if not completed.
|  | Task Detail - Notes | Textarea | “Add notes…” | No | Technician | Optional.
|  | Task Detail - Supplies | Supplies Used | Multi-row | “Add SKU + Qty” | No | Technician | Only SKUs allowed under active contract.
|  | Task Detail - Signature | Signature Pad | “Sign here” | Cond | System | Required only if template says.
|  | Task Detail - Actions | Save Draft | Button | “Save” | No | Technician | Saves partial progress.
|  |  | Complete Task | Button | “Mark Complete” | Yes | Technician | Validates template-required fields + required photos.
|  | Task Detail - Overlay | Lock Banner | Banner | “Task Locked — Check-In Required” | Yes | System | Tap → redirects to Check-In Screen.
|  |  | Lock Reason | Text | “Check-In pending” | Yes | System | Applies ONLY if contract requires check-in.
|  |  | Action When Tapped | Navigation | → Check-In | Yes | System | Automatic redirect.
| Scheduled Tasks | Future Tasks | Scheduled Tasks List | Cards | — | Yes | System | Only future tasks for active contract.
|  |  | Recurrence | Badge | “Weekly” | Yes | System | From contract recurrence.
|  |  | Next Scheduled Time | DateTime | 11/26/2025 - 10:15 AM | Yes | System | Display only.
|  |  | Status | Badge | “Locked until Schedule Window” | Yes | System | Unlocks only at scheduled window.
|  |  | Tap Action | Navigation | — | Yes | System | If locked: redirect to Check-In if check-in required. If unlocked: open Task Detail.
| Check-In (Triggered Screen, not a menu item) | Access Verification | Property | Text | “XYZ Tower” | Yes | System | Based on task’s contract mapping.
|  |  | Area | Text | “Lobby” | Yes | System | Display only.
|  |  | Instructions | Static Text | “Ask client for access code.” | Yes | System | Only if this contract requires check-in.
|  |  | Access Code | PIN Input (6-digit) | “Enter 6-digit code” | Yes | System | Validate against schedule_event.access_code.
|  |  | Verify Button | Button | “Verify & Continue” | Yes | System | On success → unlocks all tasks for this schedule_event.
|  |  | Error Message | Inline Text | “Incorrect code (2 attempts left)” | No | System | Rate-limit attempts.
| My Tickets | Ticket List | Tickets | List | — | No | Supervisor / Team Lead | Filter by ticket.contract_id == active_contract.id
|  | Ticket Detail | Title | Text | “Water leak in basement” | Yes | Supervisor | Display.
|  |  | Add Comment | Textarea | “Add update…” | No | Any | Appends to ticket history.
|  |  | Add Photo | File upload | “Attach photo” | No | Any | Validates photo rules.
|  |  | Resolve | Button | “Resolve Ticket” | Cond | Supervisor / Team Lead | Tech can resolve ONLY IF assigned_by_role in {Supervisor, TL}.
| Supply Request (Phase 3) | Request Form | Contract | Hidden / Label | active_contract.name | Yes | System | Always bound to active contract.
|  |  | Property | Dropdown | “XYZ Tower” | Yes | Technician | Only properties in active contract.
|  |  | Area | Dropdown | “Lobby” | Yes | Technician | Filtered by property.
|  |  | Item SKU | Dropdown (searchable) | “Bleach (SKU123)” | Yes | Technician | Only SKUs allowed under this contract.
|  |  | Quantity | Number | “Qty” | Yes | Technician | >0; approval if above threshold.
|  |  | Billable Label | Label/Toggle | “Included / Billable” | Cond | System | Controlled by contract’s supply_billing_rule.
|  |  | Attach Photo | File Upload | “Add photo” | No | Technician | Optional.
|  |  | Submit | Button | “Request Supplies” | Yes | Technician | Creates supply_request tied to contract.
| Notifications & Offline Sync | Sync | Sync Status | Badge | “Offline” | Yes | System | Contract-scoped queue.
|  |  | Pending Actions | Link | “3 pending actions” | No | System | Segmented by contract_id.
|  | Feed | Notification List | List | — | No | System | Filter by active_contract unless global.
| Profile | Profile Landing | Display Photo | File upload (avatar) | “Upload photo” | No | System | Max 5MB, jpg/png/heic. Optional in Phase-1. Show circular thumbnail.
|  |  | Display Name | Text input | “John Doe” | Yes | System | Max 100 chars. Updates users.name
|  |  | Mobile Number | Read-only label | “+971 5xx xxx xxxx” | Yes | System | E.164 format. Editable only via Ops Admin flow (Phase-1 read-only).
|  |  | Email | Text input | “john@client.com” | No | System | Validate email format; optional.
|  |  | Job Title / Role | Read-only label | “Technician” | Yes | System | Shown for context.
|  |  | Assigned Contracts | List (tapable) | “ABC Tower — Recurring” | Yes | System | Lists contracts user belongs to; tap to open Contract Details screen.
|  | Contract Details | Contract Name | Text | “ABC Tower – Recurring” | Yes | System | Display contract meta.
|  |  | Contract Type | Badge | “Recurring / Ad-hoc” | Yes | System | Display only.
|  |  | Contract Dates | Text | “01 Jan – 31 Dec 2026” | No | System | Display only.
|  |  | Properties (under contract) | Collapsible list | “ABC Tower > Lobby, Parking” | Yes | System | Tap property to view area list.
|  |  | x | Collapsible list | “Lobby, Restrooms” | Yes | System | Display only.
|  |  | Default Contract Selector | Dropdown | “Set as default” | No | System / Ops Admin | Set which contract auto-selects at login. Visible if user has >1 contract.
|  | Settings | Change Password | Link → Form (old/new/confirm) | — | No | System | New password rules: min 8 chars, 1 uppercase, 1 digit. Server validates.
|  |  | Two-Factor Auth (2FA) | Toggle (on/off) | “Enable 2FA (SMS)” | No | System | If enabled, send OTP and verify immediately. Persist preference.
|  |  | Preferred Language | Dropdown | “English / Arabic” | No | System | Persist locale; UI updates after restart or reload.
|  |  | Notification Preferences | Toggles (push/in-app/sms) | “Task updates / Tickets / Supply” | No | System | Default on for Task updates; if user disables push, still show in-app. SMS reserved for critical alerts.
|  |  | Location Permission Status | Label + Action | “Enabled / Disabled” | No | System | Show system permission status; link to device settings. (No GPS check-in in Phase-1).
|  |  | App Version | Label | “v1.0.3” | No | System | Display only.
|  |  | Privacy & Terms | Link | “View” | No | System | Opens web view to terms (if required).
|  |  | Accessibility Options | Links / toggles | “Large text / High contrast” | No | System | Basic accessibility toggles if supported.
|  | Account | Sign-Out / Logout | Button | “Log out” | Yes | System | Clears local cache & queues, prompts if pending offline items.
|  |  | Delete Account (Admin only) | Link | — | No | Ops Admin | Not available to technician in Phase-1.
|  | Audit / Activity | Recent Activity | List | “Completed Task — Lobby — 10:15 AM” | No | System | Optional: shows last X actions for transparency. Read-only.
|  | Contact Client Rep | Client Contact list | List / tap to call/SMS | “Site Rep: +971 5xx” | No | System | If client contact present at property, show call & SMS shortcut. Permissions & rate limits apply.
| Help & Support | Help Landing | Quick Help Topics | Accordion / List | “How to check-in / Photo limits / Offline” | No | System | Static content + links to FAQ articles. Content editable by Ops Admin.
|  |  | Contact Support (Create Ticket) CTA | Button | “Report an issue” | No | System | Opens Create Support Ticket form.
|  | Create Support Ticket | Subject | Text input | “Describe issue in short” | Yes | Technician | Max 100 chars.
|  |  | Category | Dropdown | “App Issue / Site Issue / Supply / Other” | Yes | Technician | Used for routing; categories defined by Ops Admin.
|  |  | Description | Textarea | “Detailed description…” | Yes | Technician | Max 2000 chars. Encourage steps to reproduce & site context.
|  |  | Attachments | File upload | “Add photos/screenshots” | No | Technician | Images max 5MB; up to 5 files. Attachments linked to contract_id and optional task_id / ticket_id
|  |  | Related Contract | Dropdown / Hidden (prefill) | active_contract.name | Yes | System | Prefill with active_contract if opened from contract context; allow change only if user has >1 contract and started from global menu.
|  |  | Related Property | Dropdown (filtered) | “ABC Tower - Lobby” | No | Technician | Optional, but recommended.
|  |  | Urgency / Priority | Dropdown | “Low / Normal / High” | No | Technician | If "High" may trigger SMS to Ops Admin or Supervisor.
|  |  | Submit Button | Button | “Send to Support” | Yes | Technician | On submit: create support_ticket record routed to Client Relations / Ops Admin. Show ticket number and confirmation.
|  | My Support Tickets | Ticket List | List | “SUP-1234 — App crash” | No | System | Lists support tickets created by user (filter by contract if present).
|  |  | Ticket Row Details | Title / Status / Created At | “SUP-1234 • Open” | No | System | Tap to open ticket detail.
|  | Support Ticket Detail | Title | Text | “SUP-1234: Unable to upload photo” | Yes | System | Shows full history.
|  |  | Thread / Messages | Thread UI | “Technician: I see error X” | No | System | Messages from support team and user.
|  |  | Add Message / Comment | Textarea | “Additional info…” | No | Technician | Attach images to messages; messages append to thread.
|  |  | Attach Photo | File upload | “Add screenshot” | No | Technician | Same media rules.
|  |  | Close Ticket | Button | “Close” | Cond | Technician | User can close only if support allows; server-side flag user_can_close
|  |  | Escalate | Button | “Escalate to Supervisor” | Cond | System / Ops Admin | Only if ticket category/priority meets escalation rules; may create Site Visit or alert Supervisor.
|  | Support Ticket Notifications | Push / In-app notification | Notification | “SUP-1234: Support replied” | No | System | Push if enabled in notification prefs; deep link to ticket.
|  | Feedback (post-ticket) | Rate Support | Rating input (1–5) | “Rate your support” | No | System | Optional after ticket close; feeds into Ops reporting.
|  | Contact Client Rep (from support) | Call / SMS button | Shortcut | “Call site rep” | No | System | If ticket needs client confirmation, show client contact if available.
|  | Offline Behavior | Draft Save | Auto-save/form draft | “Draft saved” | Yes (if offline) | System | If offline, allow saving ticket draft to queue; submit when online.
|  | Security & Privacy | PII Warning | Inline text | “Don’t share passwords” | Yes | System | Guidance for user.
Consolidated Menu Options - List
GLOBAL (present on most screens)
These are not a menu — they sit in the app chrome/header and affect everything.
Active Contract Selector (global header)
Control: Dropdown (searchable) / Contract Type badge / Client / Dates
Behavior: mandatory when user has >1 contract; toggles contract-scoped data refresh
Contract context shown in header
active_contract.name,type, expiration
Global data requirements
Every API call for tasks/tickets/supplies must include
contract_id == active_contract.id
1) Dashboard (Today’s Tasks)
Screens / Components:
Today’s Tasks List (cards)
Task Card (collapsed)
Task Card (expanded inline to Task Detail)
Fields / Controls (from matrix):
Property (card) — text
Area (card) — text
Task Type / Task Name — text header
Scheduled Time / Due Time — text
Status Badge — lock/to-do/in-progress
Checklist Summary (card pill) — “2/5” (only when unlocked)
Photo Count (card) — icon+count (only when unlocked)
Start Button (quick) — only visible when task unlocked & within window
Tap Action on card: opens Task Detail OR redirects to Check-In screen if locked
Lock Indicator / Locked Banner (visual only) — shows lock state, not an input
Acceptance / dev notes:
NO Access Code entry on dashboard. If locked, tapping routes to Check-In.
Tasks loaded filtered by
task.contract_id == active_contract.id
and assignment.
2) Scheduled Tasks
Screens / Components:
Scheduled Tasks List (future occurrences)
Scheduled Task Card / Recurrence summary
Fields / Controls:
Task Name
Next Occurrence / Scheduled Time (RRULE-derived)
Frequency Badge (Daily/Weekly/Monthly)
Locked Banner (shows opens at scheduled time)
Tap Action: if within window & unlocked, open Task Detail; otherwise route to Check-In when check-in required
Acceptance / dev notes:
Read-only until active window; summary only (no full checklist loaded until active window).
Contract-scoped feed: show only schedule events for active_contract.id
3) My Tickets
Screens / Components:
Tickets List (contract-scoped)
Ticket Detail modal / screen
Ticket actions (comment, attach photo, resolve — conditional)
Fields / Controls:
Ticket Title, Severity, Status
Ticket thread / comments
Add Comment textarea
Attach Photo (file upload)
Resolve button (visible only if
ticket.assigned_by_role
permits resolution by tech)
Acceptance / dev notes:
Load tickets where
ticket.contract_id == active_contract.id
AND
ticket.assigned_to_id == user_id
AND
assigned_by_role
∈ allowed set (Supervisor, Team Lead).
Server-side enforcement for resolve permissions.
4) Supply Request
Screens / Components:
Supply Request form
Supply Request list/status (optional view)
Supply request submission flow (with supervisor approval flow)
Fields / Controls:
Contract (hidden/prefill)
Property (dropdown filtered by contract)
Area (dropdown filtered by property)
SKU / Item selector (only allowed SKUs for contract)
Quantity (numeric)
Billable flag (label / toggle) — default from
active_contract.supply_billing_rule
Attach Photo
Notes
Submit button
Acceptance / dev notes:
If request > threshold or billable override → Supervisor approval required.
When launched from a task, contract/property/area prefills.
5) Notifications
Screens / Components:
Notification Feed list
Notification item detail (deep link to context)
Fields / Controls:
Notification title + time
Tap navigates to related screen (task, ticket, supply request)
Mark read (action)
Acceptance / dev notes:
Prefer contract-filtered notifications (
notification.contract_id == active_contract.id
) unless global.
6) Offline Sync
Screens / Components:
Sync Status badge / header (shows online/offline/syncing)
Pending Actions list (contract segmented)
Force Sync button / retry controls
Fields / Controls:
Last sync time label
Pending items list (each entry shows type: checklist/photo/supply/ticket)
Sync Now action
Acceptance / dev notes:
Queue items must be stored per
contract_id
and processed with priority rules.
Photos queued but may require retry if large.
7) Profile & Settings
Screens / Components:
Profile view (name, phone, email, photo)
Settings (change password, 2FA toggle, language)
Contracts list & default contract selector
Fields / Controls:
Display Name (editable)
Phone (read-only by default)
Email (editable)
Profile photo upload
Default contract selection
Logout
Acceptance / dev notes:
Contracts list shows all contracts assigned to user; default contract used at login.
8) Help / Support
Screens / Components:
Create Support Ticket form
Support ticket list / status (optional)
Fields / Controls:
Subject (text)
Description (textarea)
Attachments (photos/screenshots)
Submit button
Acceptance / dev notes:
Support tickets should include
contract_id
context when created from within an active contract.

## Menu & Field List - TEAM LEAD
User Role | Main Menu Option | Screen Group | Screen / Context | Field Label | UI Control Type | Placeholder / Example | Required? | Assigned By | Validation / Notes
Team Lead | Authentication | Sign-In | Sign-In | Phone Number | Text Input (numeric keypad) | "Enter mobile number" | Yes | System | Validate number; check user existence
|  |  | Sign-In | Password | Password Field | "Enter password" | Yes | System | Masked; min 8 chars
|  |  | Sign-In | Forgot Password | Link | "Forgot Password?" | No | System | Opens reset flow
|  |  | Sign-In | Sign-In Button | Button | "Sign In" | Yes | System | Auth → load contracts
|  | Forgot Password | Forgot Password | Phone Number | Text Input | "Enter mobile number" | Yes | System | Validate user
|  |  | Forgot Password | Send OTP | Button | "Send Code" | Yes | System | SMS OTP
|  |  | Forgot Password | OTP Input | PIN Input | "Enter OTP" | Yes | System | Validate; rate-limit
|  |  | Forgot Password | New Password | Password Input | "New password" | Yes | System | Validate policy
|  |  | Forgot Password | Confirm Password | Password Input | "Re-enter password" | Yes | System | Must match
|  |  | Forgot Password | Reset Button | Button | "Reset Password" | Yes | System | Redirect to Sign-In
|  | OTP Verification | OTP Verification | OTP Field | PIN Input | "Enter verification code" | Yes | System | Only if 2FA enabled
|  |  | OTP Verification | Resend Code | Button | "Resend" | No | System | Rate-limit
| Global Header (Not a Menu Option) | Contract Header | Contract Header | Active Contract Selector | Dropdown | "ACME HQ – Recurring" | Yes if >1 | System/Ops Admin | Reload all contract-scoped data
|  |  | Contract Header | Contract Type | Badge | "Recurring / Ad-hoc" | Yes | System | Controls check-in/SLA/supplies rules
|  |  | Contract Header | Contract Duration | Text | "Valid: Jan–Dec 2026" | Yes | System | Read-only
| Dashboard | Team Overview Cards | Team Overview | Team Tasks Summary | Card List | "7 tasks today" | Yes | System | Shows tasks for TL team
|  |  | Team Overview | Property | Text | "ACME HQ" | Yes | System | Display only
|  |  | Team Overview | Area | Text | "Floor 2 Lobby" | Yes | System | Display only
|  |  | Team Overview | Assigned Technician | Text | "Assigned: John K." | Yes | System | Tap → Tech task list
|  |  | Team Overview | Status Badge | Badge | "To Do / In Progress" | Yes | System | Task status
|  |  | Team Overview | Tap Action | Touch → Nav | — | Yes | System | Locked → Check-In
|  | Quick Filters | Filters | Filter Controls | Dropdown/Toggles | "Property / Area / Tech" | No | Team Lead | Applies across modules
| Team Tasks | Technician List | Technician List | Technician Row | List Item | "John K — On duty" | Yes | System | Shows TL technicians only
|  | Technician Task List | Technician Tasks | Task Card | Card | "Daily Mopping" | Yes | System | Tap → Task Detail or Check-In Status
|  | Single Assign | Single Assign | Assign To | Dropdown | "Select technician" | Yes | Team Lead | Technician must belong to active contract
|  |  | Single Assign | Reason | Textarea | "Reason for assigning" | Cond | Team Lead | Required only if contract.assignment_requires_reason = true
|  |  | Single Assign | Confirm Assign | Button | "Assign Task" | Yes | Team Lead | Creates assignment event + audit log
|  | Reassign | Reassign Form | Select Technician | Dropdown | "Select technician" | Yes | TL | Must belong to contract
|  |  | Reassign Form | Reason | Textarea | "Reason for reassign" | Cond | TL | Required if policy enabled
|  | Bulk Assign | Bulk Assign UI | Select Tasks | Checkbox List | — | Yes | TL | Multi-select
|  |  | Bulk Assign UI | Assign To | Dropdown | "Select technician" | Yes | TL | Contract-scoped
| Inspections | Inspection List | Inspection Tasks | Inspection Row | List | — | Yes | System | Template-based inspection list
|  | Inspection Detail | Inspection Template | Question Label | Text | "Are dispensers stocked?" | Yes | System | Template-defined
|  |  | Inspection Template | Response | Radio/Text/Dropdown | "Yes/No/N/A" | Cond | TL | Required if template marks required
|  |  | Inspection Template | Item Photo | File Upload | "Attach photo" | Cond | TL | Required for fail/critical items
|  |  | Notes | Notes | Textarea | "Add observation…" | No | TL | Optional
|  |  | Photos | Photo Upload | "Add photo" | Cond | TL | As per template
|  |  | Submit | Submit Button | "Submit Inspection" | Yes | TL | Auto-create SLA ticket if fail threshold met
| SLA Tickets | SLA Ticket List | Ticket List | Ticket Row | List | "Ticket #123 — Leak" | Yes | System | Contract-scoped
|  | SLA Ticket Detail | Ticket Meta | Title | Text | "Water leak — Basement" | Yes | System | Read-only
|  |  | Assignment | Assign Technician | Dropdown | "Select tech" | Cond | TL | Contract-bound
|  |  | Comment | Add Comment | Textarea | "Add update…" | No | TL | Optional
|  |  | Photo | Attach Photo | File Upload | "Add photo" | No | TL | Optional
|  |  | Actions | Escalate | Button | "Escalate" | Cond | TL | SLA rules
|  |  | Actions | Mark Resolved | Button | "Resolve Ticket" | Cond | TL | Requires proof if needed
| Site Visits | Create Visit | Add Visit Form | Date of Visit | Date | "11-07-2025" | Yes | TL | Required
|  |  | Add Visit Form | Type of Visit | Dropdown | "Scheduled / Emergency" | Yes | TL | Defines workflow
|  |  | Add Visit Form | Property | Dropdown/Search | "ACME HQ" | Yes | TL | Contract property
|  |  | Add Visit Form | Scope Details | Textarea | "Describe scope…" | Yes | TL | Required
|  |  | Add Visit Form | Potential WOs | Multi-select | "Window cleaning, Overflow" | No | TL | Optional
|  |  | Add Visit Form | Is Team Able to Perform | Radio | "Yes / No" | Yes | TL | If No → escalate
|  |  | Add Visit Form | Photos | File Upload | "Add photo" | No | TL | Optional
| Supply Request | Request Form | Request Form | Contract | Hidden | active_contract.name | Yes | System | Auto-bound
|  |  | Request Form | Property | Dropdown | "ACME HQ" | Yes | TL | Contract-scoped
|  |  | Request Form | Area | Dropdown | "Lobby" | Yes | TL | Filtered
|  |  | Request Form | Item SKU | Dropdown | "Bleach (SKU123)" | Yes | TL | Allowed SKUs only
|  |  | Request Form | Quantity | Number | "Qty" | Yes | TL | Mandatory
|  |  | Request Form | Billable | Toggle | "Included / Billable" | Cond | System | Contract rule
|  |  | Request Form | Attach Photo | File Upload | "Add photo" | No | TL | Optional
|  |  | Request Form | Submit | Button | "Submit Request" | Yes | TL | Insert supply_request record
| Notifications & Offline Sync | Feed | Notification List | Notification Row | List | "New SLA ticket assigned" | No | System | Deep link
|  | Sync | Sync Status | Sync Status | Badge | "Offline" | Yes | System | Contract-scoped
|  |  | Sync Status | Pending Actions | Link | "3 pending actions" | No | System | Offline queue
| Profile | Profile Landing | Profile Landing | Display Photo | File Upload | "Upload photo" | No | System | Optional
|  |  | Profile Landing | Display Name | Text Input | "Mary L." | Yes | System | Update
|  |  | Profile Landing | Mobile Number | Read-only | "+971 5xx" | Yes | System | Not editable
|  |  | Profile Landing | Email | Text Input | "mary@client.com" | No | System | Optional
|  |  | Profile Landing | Job Title / Role | Label | "Team Lead" | Yes | System | Display only
|  |  | Profile Landing | Assigned Contracts | List | "ACME HQ – Recurring" | Yes | System | Tap → Contract Details
|  | Contract Details | Contract Details | Contract Name | Text | "ACME HQ – Recurring" | Yes | System | Display only
|  |  | Contract Details | Contract Type | Badge | "Recurring / Ad-hoc" | Yes | System | Display only
|  |  | Contract Details | Contract Dates | Text | "01 Jan – 31 Dec 2026" | No | System | Display only
|  |  | Contract Details | Properties | Collapsible List | "ACME HQ > Lobby" | Yes | System | Tap property → area list
|  |  | Contract Details | Areas | Collapsible List | "Lobby / Parking" | Yes | System | Display only
|  |  | Contract Details | Default Contract Selector | Dropdown | "Set as default" | No | System | Visible only if >1 contract
|  | Settings | Settings | Change Password | Link → Form | — | No | System | Old/new/confirm; server validation
|  |  | Settings | Two-Factor Authentication | Toggle | "Enable 2FA (SMS)" | No | System | OTP verification required
|  |  | Settings | Notification Preferences | Toggles | "Tasks / Tickets / Supplies" | No | System | Per-user preferences
|  |  | Settings | App Version | Label | "v1.0.3" | No | System | Display only
|  |  | Settings | Privacy & Terms | Link | "View" | No | System | WebView link
|  |  | Settings | Accessibility Options | Toggles/Links | "Large text / High contrast" | No | System | Optional
|  | Account | Account | Sign-Out / Logout | Button | "Log out" | Yes | System | Clear cache; warn if offline data pending
|  |  | Account | Delete Account | Link | — | No | Ops Admin | Not shown to TL
|  | Audit / Activity | Audit / Activity | Recent Activity | List | "Reassigned Task — 10:15 AM" | No | System | Read-only audit history
|  | Contact Client Rep | Contact Client Rep | Client Contact List | Tap-to-call/SMS | "Site Rep: +971 5xx" | No | System | Shortcut if linked to property
|  | Help Landing | Help Landing | Quick Help Topics | Accordion/List | "How to inspect / Check-in steps" | No | System | Static content
|  |  | Help Landing | Contact Support CTA | Button | "Report an issue" | No | System | Opens support form
| Help & Support | Create Support Ticket | Support Form | Subject | Text Input | "Describe issue…" | Yes | Team Lead | Max 100 chars; mandatory
|  |  | Support Form | Category | Dropdown | "App Issue / Site Issue / Supply / Other" | Yes | Team Lead | Determines routing to Ops/Admin
|  |  | Support Form | Description | Textarea | "Details…" | Yes | Team Lead | Max 2000 chars; required
|  |  | Support Form | Attachments | File Upload | "Add screenshots" | No | Team Lead | Up to 5 files; up to 5MB each
|  |  | Support Form | Related Contract | Dropdown / Prefill | active_contract.name | Yes | System | Auto-filled; editable if TL has >1 contract
|  |  | Support Form | Related Property | Dropdown | "ACME HQ - Lobby" | No | Team Lead | Optional field
|  |  | Support Form | Urgency | Dropdown | "Low / Normal / High" | No | Team Lead | HIGH sends alert to Ops
|  |  | Support Form | Submit Button | Button | "Send to Support" | Yes | Team Lead | Creates support_ticket entry
|  | My Support Tickets | Ticket List | Ticket Row | List | "SUP-1234 — Open" | No | System | Filter results by active contract
|  | Ticket Detail | Ticket Detail | Title | Text | "SUP-1234: App issue" | Yes | System | Display ticket metadata
|  |  | Ticket Detail | Thread | Thread UI | — | No | System | Full message history with timestamps
|  |  | Ticket Detail | Add Comment | Textarea | "Add update…" | No | Team Lead | Optional; appends to message thread
|  |  | Ticket Detail | Attach Photo | File Upload | "Upload screenshot" | No | Team Lead | Optional; max file size limit
|  |  | Ticket Detail | Close Ticket | Button | "Close Ticket" | Cond | Team Lead | Only enabled if user_can_close = true
|  |  | Ticket Detail | Escalate | Button | "Escalate" | Cond | Team Lead | Follows SLA escalation rules
|  | Notifications | Support Notifications | Notification Row | List | "Support replied" | No | System | Deep link to ticket detail
|  | Offline Behavior | Offline Drafts | Draft Save | Auto-save | "Draft saved" | Yes (if offline) | System | Added to offline sync queue
|  | Security & Privacy | Security | PII Warning | Inline Text | "Do not share passwords" | Yes | System | Static compliance warning
TEAM LEAD — DETAILED APP FLOW & ACCEPTANCE CRITERIA
This is an end-to-end behavioral spec for TL actions, validations, edge cases and QA acceptance checks. Use it for dev acceptance criteria and QA scripts.
A. Start / Auth / Contract selection
1
Acceptance:
GET /me
returns
teams[]
and
contracts[]
. TL cannot access contract-scoped menus until a contract is selected.
2
Acceptance: switching contract reloads properties, schedules, team members, SKUs.
B. Dashboard (Team Overview)
TL sees a top summary (tasks today, open SLA tickets, inspections due). Default filter = TL’s team + Today.
Card behaviour:
C. Team Tasks / Assign & Reassign
Assign / Bulk Assign:
Permissions:
D. Inspections (primary TL function)
Open Inspection: TL selects inspection task → inspection form loads template published in Admin Console. Template fields can be text, dropdown, rating, photo, signature (if enabled).
Rules:
score < 4 → auto-ticket (standard 5-day SLA when score ==3; critical 24-hour SLA when score ≤2).
On Submit:
Acceptance tests:
E. SLA Ticket lifecycle (TL responsibilities)
TL views SLA list filtered by contract and by tickets assigned to TL or TL’s team.
TL can:
SLA alerts:
F. Site Visits (ad-hoc)
TL can create a Site Visit using fields derived from the Google / Quickbase forms you provided (date, location, type, scope, potential WOs, photos).
Workflow:
Acceptance:
G. Schedule Engine (TL interaction)
TL can create schedule events for their team (subject to Ops Admin policy). For Phase-1 TL can:
Validation:
H. Supplies & Inventory
TL may submit supply requests for active_contract properties:
Inventory integration (if enabled): check stock before approval; soft-reserve items.
I. Offline behavior & sync
TL must be able to:
Sync resolution:
J. Notifications & Escalation rules
Push/in-app/email per user preferences. High-priority tickets and emergency site visits trigger SMS to configured contacts.
Escalation follows SLA chain in docs: Technician → TL → Supervisor → Ops Admin → Senior Admin.
K. Audit & Compliance
Every TL action (assign, reassign, inspect, create visit, escalate, approve supply) creates an audit row with
actor_id
,
action
,
timestamp
,
contract_id
,
meta
. This is required for compliance & reporting.
L. Edge cases & error handling
Attempt to assign technician not in contract → blocked with message: “Technician not assigned to this contract.”
Attempt to submit inspection without required photo → inline error referencing field name.
SLA timer breach while TL offline → on next sync, server marks SLA breached and notifies Ops.
Site Visit created with missing mandatory fields (e.g., Type) → block submit.

## High Level Modules (hidden)
Modules
User Management | mobile
Clinics Management | web | 2 months
Appointment Management | web
Vendor Management | web
App Management - Super Admin
Data Management
Lead Management
Campaign/ Promotion Management
User Behavioral Recommendation System (AI Assisted)
Analytics & Reporting

## Resources (hidden)
Resource Name | Number Of Resources | Hours
Hybrid Developer - Senior Full Stack | 1 | 304
Web App - Frontend Full Stack Developer | 1 | 304 |  | 160
Web App - Backend Senior Laravel Developer | 1 | 272 |  | 1280
Senior Dev Ops | 1 | 84 | 32
Software Testing | 1 | 105
Senior Data Engineer | 1 | 75
Data Scientist | 1 | 136
Total Hours |  | 1280 |  | 0
** Deployment to production/ live environment will be handled separately
Resource Name | Number Of Resources | Hours |  | 82
Hybrid Developer - Senior Full Stack | 1 | 210 |  | 656
Web App - Frontend Full Stack Developer | 1 | 210
Web App - Backend Senior Laravel Developer | 1 | 120
Senior Dev Ops | 1 | 42
Software Testing | 1 | 75
Total Hours |  | 657
** Above hours are derived based on reusing modules from MVP 1 and hence MVP 2 can be initiate only after completion of MVP 1
** Deployment to production/ live environment will be handled separately

## Estimates Canabis App (hidden)
Feature | As a | I need to be able to | Hybrid | Web App | Backend | QA | Total
Manufacturer Profile & Config | Manufacturer | Name, Address, Contact Details, Description Set delivery radius (zip codes) | 1 | 1 | 0.5 | 0.5 | 3
Product Management | Manufacturer | Create a product - name - description - size (unit size in gm, ml, etc.) - price per unit - images | 1 | 4 | 1 | 3 | 9
List all my products
Update a product
Delete a product
Sales | Manufacturer | View all order received - customer details - products details - total amount - payment status - payment mode - offer applied | 1 | 5 | 2 | 3 | 11
Mark order status (sold/cancelled)
View sales report - date wise - product wise - customer wise
View order received notifications
Reviews | Manufacturer | View a list of reviews - review text - user account - ratings - timestamp | 0.5 | 1 | 0.5 | 0.5 | 2.5
Product List | User | View a list of all products - name, short description, image, price, ratings - search - filter: product type - sort - scroll pagination - Add to cart button | 4 | 2 | 2 | 3 | 11
View Product Details - name, short description, image, price, comparison, reviews & ratings - Add to cart button
Cart Management | User | Add product to cart | 4 | 1 | 2 | 3 | 10
View cart - products - quantity/product - price/unit - amount/product - total product count - total amount - discount if any - tax etc
Update product quantity
Apply or remove coupons/offers - view a list of all offers from the manufacturer
Make payment
Order Management | User | View my orders | 3 | 1 | 1 | 2 | 7
View order details
Cancel an order - reason for cancellation
Payments |  | Make a payment | 3 | 2 | 2 | 3 | 10
View my payment history
Reviews | User | Add product review - review text - rating from 1 to 5 | 2 | 0.5 | 0.5 | 1 | 4
View all my reviews and ratings
Order Processing | System | Generate different orders for each manufacturer |  |  | 2 | 1 | 3
Integrating common modules from MVP 1 | System | All common modules from MVP 1 should be reused in MVP 2, with required adjustments - user authentication - manufacturer authentication - Deals and offers management (manufacturer) - Deals and offers view (users) - User notifications - Manufacturer notifications | 3 | 3 | 2 | 3 | 11
|  |  | Total Efforts (In days) |  |  |  | 81.5
1. Yelp API integration is not included, as this would be handled at scraper level 2. There are some features, e.g. authentication, deals & offers, notifications, which are not fully estimated here. These will be taken from MVP 1 and adjusted as per requirements.

## Menu & Field List - CLIENT
User Role | Main Menu Option | Screen Group | Screen / Context | Field Label | UI Control Type | Placeholder / Example | Req? | Assigned By | Validation / Notes
Client | Authentication | Sign-In | Sign-In | Phone Number | Text Input (numeric keypad) | "Enter mobile number" | Yes | System | Validate number; check client exists
|  |  | Sign-In | Password | Password Field | "Enter password" | Yes | System | Masked; min 8 chars
|  |  | Sign-In | Forgot Password | Link | "Forgot Password?" | No | System | Opens reset flow
|  |  | Sign-In | Sign-In Button | Button | "Sign In" | Yes | System | Auth → load client sites + contracts
|  | Forgot Password | Forgot Password | Phone Number | Text Input | "Enter mobile number" | Yes | System | Must exist
|  |  | Forgot Password | Send OTP | Button | "Send Code" | Yes | System | SMS OTP
|  |  | Forgot Password | OTP Input | PIN Input | "Enter OTP" | Yes | System | Validate OTP
|  |  | Forgot Password | New Password | Password Input | "Create new password" | Yes | System | Min 8 chars
|  |  | Forgot Password | Confirm Password | Password Input | "Re-enter password" | Yes | System | Must match
|  |  | Forgot Password | Reset Password | Button | "Reset Password" | Yes | System | Redirect to Sign-In
| Dashboard | Service Overview | Dashboard Summary | Completion % | Progress Bar | "65% Completed" | Yes | System | Auto-calculated
|  |  | Dashboard Summary | Ongoing Tasks | List | "2 tasks in progress" | Yes | System | Contract-scoped
|  |  | Dashboard Summary | Completed Tasks | List | "12 tasks completed" | Yes | System | Last 24 hrs
|  |  | Ongoing Tasks List | Task Row | List | "Daily Cleaning — Lobby" | No | System | Tap → Task Detail (Client View)
|  |  | Ongoing Tasks List | Start Time | Text | "Started: 10:15 AM" | No | System | Fetched from technician logs
|  |  | Ongoing Tasks List | Status | Badge | "In Progress" | No | System | Maps task state
|  | Task Detail | Task Detail | Property | Text | "ACME HQ" | Yes | System | Read-only
|  |  | Task Detail | Area | Text | "Floor 2 Lobby" | Yes | System | Read-only
|  |  | Task Detail | Checklist Summary | Text | "3/5 Completed" | No | System | Read-only
|  |  | Task Detail | Technician Notes | Text | "Floor corners cleaned…" | No | System | Visible if provided
|  |  | Task Detail | Photos | Image Preview | — | No | System | Proof images (read-only)
|  |  | Task Detail | Timestamp | Text | "Completed: 11:02 AM" | No | System | Auto-generated
| Feedback | Submit Feedback | Feedback Form | Rating (1–5) | Star/Number Input | "Rate 1–5" | Yes | Client | Mandatory
|  |  | Feedback Form | Descriptive Rating | Dropdown | "Satisfactory / Somewhat Satisfactory / Unsatisfactory" | Yes | Client | Required
|  |  | Feedback Form | Comments | Textarea | "Describe your concern…" | No | Client | Optional
|  |  | Feedback Form | Attachments | File Upload | "Add photo/video" | No | Client | Max 5 files
|  |  | Feedback Form | Submit | Button | "Submit Feedback" | Yes | Client | Creates feedback record
|  | View History | Feedback Log | Feedback Row | List | "⭐ 3 - Somewhat Satisfactory" | No | System | Sort by date
|  |  | Feedback Log | Timestamp | Text | "Submitted: 3:12 PM" | No | System | Display only
|  |  | Feedback Detail | Rating | Badge | "3 — Somewhat Satisfactory" | Yes | System | Read-only
|  |  | Feedback Detail | Photos | Image Preview | — | No | System | If uploaded
| Tickets | Ticket List | Ticket List | Ticket Row | List | "Ticket #123 — Leak" | No | System | Filter by client sites
|  |  | Ticket List | Status | Badge | "In Progress / Closed" | Yes | System | SLA-based
|  | Ticket Detail | Ticket Detail | Title | Text | "Restroom not cleaned" | Yes | System | Read-only
|  |  | Ticket Detail | SLA Progress | Progress Bar | "2 days remaining" | Yes | System | Auto-calculated
|  |  | Ticket Detail | Description | Text | "Reported cleanliness issue" | No | System | Read-only
|  |  | Ticket Detail | Photos | Image Preview | — | No | System | If provided
|  |  | Ticket Actions | Reopen Ticket | Button | "Reopen Issue" | Cond | Client | Only if status=Closed
|  |  | Ticket Actions | Create Sub-Ticket | Button | "Report Repeat Issue" | No | Client | Links to Sub-ticket form
|  | Sub-Ticket Form | Sub-Ticket Form | Description | Textarea | "Describe repeat issue…" | Yes | Client | Required
|  |  | Sub-Ticket Form | Photos | File Upload | "Attach proof" | No | Client | Optional
|  |  | Sub-Ticket Form | Submit | Button | "Submit Sub-Ticket" | Yes | Client | Creates sub-ticket tied to parent
| SLA | SLA Overview | SLA List | SLA Row | List | "Ticket #123 — 60% remaining" | No | System | Sorted by severity
|  | SLA Detail | SLA Detail | SLA Countdown | Progress Bar | "50% — 2.5 days left" | Yes | System | Auto-updating
|  |  | SLA Detail | Severity | Badge | "Standard / Critical" | Yes | System | Based on inspection score
|  |  | SLA Detail | Timeline | List | "Technician updated proof" | No | System | Read-only history
| Notifications | Notification Feed | Notification List | Notification Row | List | "Your issue is resolved" | No | System | Deep link to SLA/Task
|  |  | Notification List | Timestamp | Text | "Today, 2:41 PM" | No | System | Display only
| Profile | Profile Landing | Profile | Display Name | Text Input | "Veronica Duarte" | Yes | Client | Editable
|  |  | Profile | Phone Number | Read-only | "(713) 943-6300" | Yes | System | Non-editable
|  |  | Profile | Email | Text | "veronica@acme.com" | No | Client | Email validation
|  |  | Profile | Linked Sites | List | "1155 Edgebrook Dr" | Yes | System | Contract-bound
|  |  | Profile | Preferred Language | Dropdown | "English / Spanish" | No | Client | Changes UI locale
|  | Settings | Settings | Notification Preferences | Toggles | "Task updates / SLA updates" | No | Client | Optional
|  |  | Settings | Privacy & Terms | Link | "View" | No | System | Opens WebView
|  | Account | Account | Logout | Button | "Log out" | Yes | Client | Clears client session
| Help & Support | Help Landing | Help Topics | Quick Help | List | "How to submit feedback" | No | System | Static
|  | Contact Support | Support Form | Subject | Text Input | "Describe issue…" | Yes | Client | Required
|  |  | Support Form | Description | Textarea | "Explain problem…" | Yes | Client | Required
|  |  | Support Form | Attachments | File Upload | "Attach screenshot" | No | Client | Optional
|  |  | Support Form | Submit | Button | "Send" | Yes | Client | Creates support_ticket
|  | Support History | Ticket List | Ticket Row | List | "SUP-789 — Closed" | No | System | Filtered by client
|  | Support Detail | Support Detail | Thread | Thread UI | — | No | System | Replies from Ops